## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
No | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | Login with Google | Welcome | Medium | Iteration 1 | SE150351 | Phan Thị Tố Quyên | Iteration 1 | 1
2 | Post blog | Write blog | Simple | Iteration 1 | SE150412 | Hồ Tấn Thành | Iteration 1 | 2
3 | Create user | Welcome | Simple | Iteration 1 | SE150338 | Nguyễn Quốc Lộc | Iteration 2
4 | Edit blog | View blog | Simple | Iteration 1 | SE150421 | Nguyễn Thành Tâm | Iteration 2
5 | Delete blog | View blog | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong | Iteration 1 | 3 |  |  | 60
6 | Search blog by major | Home page | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong | Iteration 1 | 4 | 3 |  | 120
7 | Search blog by subject | Home page | Simple | Iteration 1 | SE150412 | Hồ Tấn Thành | Iteration 1 | 5 |  |  | 240
8 | Search blog by title | Home page | Simple | Iteration 1 | SE150338 | Nguyễn Quốc Lộc | Iteration 1 | 6
9 | Sort blog by vote | Home page | Simple | Iteration 1 | SE150421 | Nguyễn Thành Tâm | Iteration 1 | 7 | 4
10 | Sort blog by date | Home page | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên | Iteration 1 | 8
11 | Vote blog | View blog | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên | Iteration 2 | 9 | 5
12 | View number of vote | View blog | Simple | Iteration 1 | SE150412 | Hồ Tấn Thành |  | interation 2 | của mentor page | Vote Rating
13 | View blog detail | View blog | Simple | Iteration 1 | SE150338 | Nguyễn Quốc Lộc | Iteration 1
14 | Comment | View blog | Simple | Iteration 1 | SE150421 | Nguyễn Thành Tâm | Iteration 1 | 10 | 6
15 | Give feedback | Give feedback | Complex | Iteration 1 | SE150351 | Phan Thị Tố Quyên | Iteration 1 | 11 | 7
16 | Give feedback about Mentor | Give feedback | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong |  | cần xem xét
17 | View draft blog | Manage draft blog | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
18 | Delete draft blog | Manage draft blog | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
19 | Mentor register | Mentor register | Simple | Iteration 2 | SE150421 | Nguyễn Thành Tâm |  | v
20 | View profile | Manage profile | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên | Iteration 2
21 | view personal page | Manage profile | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong | Iteration 2
22 | Edit profile | Manage profile | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
23 | View history activity list | Manage activity | Medium | Iteration 2 | SE150351 | Phan Thị Tố Quyên | Iteration 2
24 | View history activity detail | Manage activity | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
25 | Delete activity | Manage activity | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên | Iteration 2 | Hỏi ý kiến cô
26 | Search activity | Manage activity | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
27 | Logout | Home page | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành | Iteration 2
28 | Approve blog | Approve blog | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
29 | View approve blog list | Approve blog | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên | Iteration 2
30 | View approve blog detail | Approve blog | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên | Iteration 2
31 | View vote list | Vote rating | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
32 | Sort vote | Vote rating | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
33 | Give award | Vote rating | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
34 | Ban account | Manage account | Simple | Iteration 2 | SE150421 | Nguyễn Thành Tâm | Iteration 2 | v
35 | Unban account | Manage account | Simple | Iteration 2 | SE150407 | Nguyễn Thành Tâm | Iteration 2 | v
36 | View user activities | User details | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
37 | View account list | Manage account | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
38 | Process user requests | Mentor register | Simple | Iteration 3 | SE150338 | Nguyễn Quốc Lộc |  | từ mentor register -> admin page
39 | View feedback list | Feedback List | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm |  | v
40 | View feedback detail | Feedback details | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm
41 | Search feedback | Feedback List | Simple | Iteration 3 | SE150407 | Nguyễn Thái Phong
42 | Create major | Manage major | Simple | Iteration 3 | SE150412 | Hồ Tấn Thành
43 | View major list | Manage major | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên | Iteration 2
44 | Edit major | Manage major | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm |  | v
45 | Delete major | Manage major | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên | Iteration 2
46 | Search major | Manage major | Simple | Iteration 3 | SE150407 | Nguyễn Thái Phong
47 | Create subject | Manage subject | Simple | Iteration 3 | SE150412 | Hồ Tấn Thành
48 | View subject list | Manage subject | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên | Iteration 2
49 | Edit subject | Manage subject | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm |  | v
50 | Delete subject | Manage subject | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên | Iteration 2
51 | Search subject | Manage subject | Simple | Iteration 3 | SE150407 | Nguyễn Thái Phong
52 | Logout | Admin page | Simple | Iteration 3 | SE150412 | Hồ Tấn Thành | Iteration 2
53 | System notifies | System handler | Simple | Iteration 3 | SE150338 | Nguyễn Quốc Lộc
54 | System send mail | System handler | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm |  | v
55 | Notify errors | Notify Errors | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên | Iteration 1 | 12 | 8
56 | Get all blogs | Get blogs | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên | Iteration 1 | 13 | 9